## UAT checklist
Phase | Topic | What to do | Done | Notes
Before the UAT | Scope | Agree which processes and user stories are in the UAT, and write down what is not.
Before the UAT | Scope | Name an owner from the business for each process: the person who signs off.
Before the UAT | Scope | Agree what Critical, High, Medium and Low mean before the first issue is logged.
Before the UAT | Test cases | Write one test case per business scenario, in the words of the people who test it.
Before the UAT | Test cases | Give every step an action and an expected result, and test data where it matters.
Before the UAT | Test cases | Mark each test case Must, Should or Could, so the important ones are tested first.
Before the UAT | Test cases | Add the unhappy paths: a wrong value, a missing field, a user without the right role.
Before the UAT | Test cases | Check that every user story in scope has at least one test case.
Before the UAT | Test cases | Let a key user from the business review the scripts before the test days.
Before the UAT | Testers | Choose testers who do the work every day, from every team that uses the system.
Before the UAT | Testers | Give each tester a group and their own scripts.
Before the UAT | Testers | Block the test days in their calendars and free them from their daily work.
Before the UAT | Testers | Brief them in half an hour: how to record a result and how to log an issue.
Before the UAT | Environment and test data | Prepare a test environment that looks like production: configuration, integrations and data.
Before the UAT | Environment and test data | Create a test account for every role, and check that each one can sign in.
Before the UAT | Environment and test data | Load the test data: customers, products, price lists and open records.
Before the UAT | Environment and test data | Use test data instead of customer data wherever you can.
Before the UAT | Environment and test data | Agree when fixes are deployed to the test environment during the test days.
Before the UAT | Schedule | Plan the test days in blocks, with a fixed time for the triage every day.
Before the UAT | Schedule | Keep time for a retest round after the fixes.
Before the UAT | Schedule | Set the date of the go/no-go meeting, and invite the steering committee now.
Before the UAT | Schedule | Check the release calendar of Salesforce or Dynamics 365: a platform release in the middle of your UAT changes what you test.
Before the UAT | Entry criteria | The system test is done, and no Critical defect from it is still open.
Before the UAT | Entry criteria | The test environment, the test accounts and the test data are ready.
Before the UAT | Entry criteria | The business has reviewed the test cases.
Before the UAT | Entry criteria | Every tester has been invited and has signed in once.
During the UAT | Daily stand-up | Start each day with fifteen minutes: what was tested, what blocks, what is planned today.
During the UAT | Daily stand-up | Compare progress per group with the plan, and move testers where they are needed.
During the UAT | Logging issues | Log one issue per problem, with the step, what you expected and what happened instead.
During the UAT | Logging issues | Add a screenshot and the link to the record.
During the UAT | Logging issues | Look for an existing issue first, so the same problem is not logged twice.
During the UAT | Logging issues | Make sure every failed step has an issue, or a reason why not.
During the UAT | Triage | Hold the triage every day, with the business and the development team together.
During the UAT | Triage | Give each new issue a severity, a priority and someone who fixes it.
During the UAT | Triage | Decide for each one: fix it, reject it, or turn it into a change request.
During the UAT | Triage | Put change requests on the backlog, not into this release.
During the UAT | Retests | Let the tester who found the issue retest it once the fix is deployed.
During the UAT | Retests | Write down which release and build each retest was done on.
During the UAT | Retests | Start a new round after a large fix, and test the processes around the fix again.
Closing the UAT | Exit criteria | Every Must test case has passed.
Closing the UAT | Exit criteria | No Critical issue is open.
Closing the UAT | Exit criteria | Every open High issue has a workaround or a date for the fix that the business accepts.
Closing the UAT | Exit criteria | Every test case in scope has a result.
Closing the UAT | Sign-off | Ask the owner of each process to sign off: accepted, accepted with conditions, or rejected.
Closing the UAT | Sign-off | Write down every condition, with who does it and by when.
Closing the UAT | Go/no-go | Hold the go/no-go meeting with the figures on the screen, not from memory.
Closing the UAT | Go/no-go | Record the decision, the conditions and who took it.
Closing the UAT | The report | Say what was in scope, and what was not tested.
Closing the UAT | The report | Show the results per group and per priority, and the release and build that were tested.
Closing the UAT | The report | List the open issues by severity, with the decision on each one.
Closing the UAT | The report | Add the sign-offs, with their conditions.
Closing the UAT | The report | Name the known risks and workarounds for the first weeks after go-live.
Closing the UAT | After the go-live | Keep the test cases: they are the regression test for the next CRM release.
Closing the UAT | After the go-live | Write down what to do differently in the next UAT, while it is fresh.

## About
UAT checklist for a CRM go-live
What to arrange before, during and after the user acceptance test of a new CRM or a big release. Each item is one thing to do. Use it as it is, or as the start of your own test plan.
UAT Studio does most of this list for you. The readiness check shows what is missing before the test day, testers sign in with a code and see only their own scripts, a failed step becomes an issue with a screenshot, the triage runs on a shared screen, and the go/no-go report is ready when the last result is in. Try it on your own project with a free 14-day pilot.
https://uat.studio/guides/uat-checklist/
https://uat.studio/